## Sheet1
Artifact | Key Milestones | Action | Start Date | Target Date | Responsible Party | Status | Notes | Not Started | Complete | In Progress | On Hold
* | * | Draft Domain Space Sub-Committe Onboarding POA&M |  |  | Prospective Sub-Committee & NBAC TSC
|  | Plan Meetings for Collaboration & POA&M updates |  |  | Prospective Sub-Committee & NBAC TSC
|  | Schedule Meetings for Collaboration & POA&M updates |  |  | Prospective Sub-Committee & NBAC TSC
|  | Create (Collaboration) Site for Document Sharing |  |  | Prospective Sub-Committee & NBAC TSC Chair/Co-Chair |  | This can occur after the Sub-Committe is formally Stood up
* | * | Register individual & Entity Contributor Lisence Agreements |  |  | Prospective Sub-Committee
* | * | Draft/Complete Business Need Template |  |  | Prospective Sub-Committee
| * | Identify Stakeholders |  |  | Prospective Sub-Committee
* |  | Prepare a list of Stakeholders & Sub-Committee Members (Roster) |  |  | Prospective Sub-Committee
| * | Develop Value Proposition |  |  | Prospective Sub-Committee
|  | Identify Potential Use Cases for Exchanges |  |  | Prospective Sub-Committee
|  | Identify Prospective Model Content |  |  | Prospective Sub-Committee
| * | Identify Sub-Committee Governace Principals (Executives/Senior Leaders, Chair/Co-Chairs, Secretary, NBAC TSC Voting Members, Technical Lead/Model Developer, Harmonization Representatives) |  |  | Prospective Sub-Committee
| * | Determine Organizational Steakholders/Resource Patrons |  |  | Prospective Sub-Committee
| * | Conduct Periodic Progress Reviews with NBAC TSC Co-Chairs |  |  | Prospective Sub-Committee & NBAC TSC Chair/Co-Chair
|  | Propose Tentative date for Sub-Committee presentation/proposal to NBAC TSC |  |  | Prospective Sub-Committee
| * | Confirm Date for Presentation to NBAC TSC |  |  | NBAC TSC Chair/Co-Chairs
* |  | Draft Sub-Committee Governance Document |  |  | Prospective Sub-Committee
|  | Create Sub_Committee Web presence on NIEM.org/NIEM.gov |  |  | NMO TSC/STRATCOM/OASIS |  | This can occur after the Sub-Committe is formally Stood up
* | * | Create Brief for NBAC TSC Proposing New Sub-Co0mmittee
| * | Brief NBAC TSC |  |  | Prospective Sub-Committee
| * | Endorse or reject Proposal |  |  | NBAC TSC Chair/Co-Chairs
| * | Notify PGB and Prospective Sub-Committee of Endorsement |  |  | NBAC TSC Chair/Co-Chairs
| * | Stand Up Domain |  |  | Sub-Committee
* | * | Publish Sub-Committee Governance Document |  |  | Prospective Sub-Committee |  | This can occur after the Sub-Committe is formally Stood up
* | * | Publish Sub-Committee Roster |  |  | Prospective Sub-Committee |  | This can occur after the Sub-Committe is formally Stood up
| * | Appoint NBAC TSC Voting Members
|  | Develop Communications and Marketing Plan (Web, Linkedin, Twitter, trade pubs, …) |  |  | NMO TSC/STRATCOM/OASIS |  | This can occur after the Sub-Committe is formally Stood up
|  | Conduct Domain Kickoff Mtg |  |  | Sub-Committee
|  | Conduct Periodic Domain Meetings |  |  | Sub-Committee
|  | Hold Domain Symposium |  |  | Sub-Committee
|  | Participate in Monthly NBAC TSC Meetings |  |  | Sub-Committee
|  | Assign individuals to carry out governance and operations responsibilities |  |  | Sub-Committee
|  | Hold initial governance group meetings |  |  | Sub-Committee
|  | Notify the initially identified stakeholders that the Sub-Committee and Domain Space has been established and inform them of any upcoming domain activities |  |  | Sub-Committee
|  | Invite Stakeholders to attend NBAC Meetings |  |  | Sub-Committee
|  | Update POA&M to Reflect On-going Operations |  |  | Sub-Committee
| * | Identify/submit conent for inclusion in model version |  |  | Sub-Committee
| * | Participate in Model Harmonization |  |  | Sub-Committee