## Sheet1
Task Name | % Complete | Status | Duration | Notes | Predecessors
NIEM Transition | 61% | On Schedule | 544 days?
Preparation | 76% | On Schedule | 283 days?
Due Diligence | 100% | Complete | 66 days?
NBAC/NTAC Endorsement | 100% | Complete | 1 day
ESC Approval | 100% | Complete | 1 day
Transition Team Standup | 100% | Complete | 25 days
Transition Kickoff | 100% | Complete | 1 day
Setup Battle Rhythm | 100% | Complete | 1 day
Due Diligence Complete | 100% | Complete | 1 day |  | 4,5,6,7,8
Create New Governance | 28% | On Schedule | 283 days?
Draft Charter | 100% | Complete | 1 day | Sent to NBAC & NTAC co-chairs for input
Charter Approval | 100% | Complete | 1 day
Submit Charter to OASIS | 100% | Complete | 1 day
Prepare a list of NIEM assets (website, GitHub repos, mailing lists, etc.) that will transition into the Open Project (NIEM staff) | 0% | On Schedule
Document/review NIEM staffing requirements | 0% | On Schedule
Review NIEM assets and determine what modifications, if any, are needed to brand them or transition them to the OASIS Open Project | 0% | On Schedule
Prepare a list of existing NIEM governance/process documents | 25% | On Schedule |  | Loaded most in intellink
Revise NIEM governance over to OASIS | 0% | On Schedule
Determine how to organize/revise existing NIEM governance/process documents over to the Open Project | 0% | On Schedule
Sponsorship | 50% | On Schedule | 2 days
Create List of Sponsors | 100% | Complete | 1 day | Katherine has a starter list of Sponsors
Recruit additional Sponsors | 0% | Future Task | 1 day |  | 21
Marketing & Development | 0% | On Schedule | 1 day?
Comms Plan | 0% | Future Task | 1 day?
Awareness Campaign | 0% | Future Task | 1 day? |  | 24
Development Domain Stewardship Transition Workshops | 0% | On Schedule
Governance Complete | 0% | On Schedule |  |  | 11,12,13,14,15,16,17,18,19,22,25,26,23
Preparation Complete | 0% | Future Task | 0 days |  | 3,10
Formal Transition to OASIS | 0% | Future Task | 262 days?
Formal Transition | 0% | Future Task | 262 days?
Set up formal PGB | 0% | Future Task |  | Dependant on Sponsorship, Potential PGB first meeting January 2023
Mentor NIEM OASIS PGB | 0% | Future Task
Selected Technology Capital Transferred (MEP tool, NIEM model, etc) | 0% | Future Task
Intellectual Capital Transferred (goverance docs, github docs, etc) | 0% | Future Task
Host Domain Stewardship Transition Workshops | 0% | Future Task
Final ESC Turnover to PGB | 0% | Future Task
Formal Trasition Complete | 0% | Future Task | 0 days |  | 31,32,33,34,36
NIEM NMO transition to OASIS | 0% | Future Task | 262 days? |  | 29
Enterprise Tools | 0% | Future Task
Training | 0% | Future Task
Annual Model Update | 0% | Future Task
NIEM Management Office | 0% | Future Task
Meeting Management | 0% | Future Task
NIEM OASIS Standard Complete | 0% | Future Task | 0 days |  | 39,40,41,42,43