## Summary
OVERVIEW |  | TASKS
| Est (days) |  | Est (days)
NIEM 6.1 PSD01 | 13 | NIEM 6.1 PSD01 | 13
NIEM API 2.0 | 25.5 | Add new domains | 4.5
NIEM Toolbox | 4.5 | Analytical Laboratory | 1.5
NTAC Support | 6 | Forensics | 1.5
Miscellaneous | 5 | Identity Management | 1.5
Grand Total | 54 | Update existing content | 4
|  | Biometrics | 1
|  | FBI code updates | 1
| Est (days) | MilOps (EMS CR) | 0.5
Christina | 45 | Other (TBD) | 1.5
Tom | 9 | Other model tasks | 4.5
Grand Total | 54 | Facilitate or assist in public review meetings | 1
|  | Miscellaneous | 1.5
|  | Update specification document | 1
|  | Update websites | 1
|  | NIEM API 2.0 | 25.5
|  | QA | 6
|  | Implement model QA | 3
|  | Implement change request spreadsheet QA | 3
|  | Update database content | 8.5
|  | Implement user permissions | 3
|  | Initialize new version | 0.5
|  | Load change request spreadsheet | 3
|  | Load CMF into database | 1
|  | Load migration rules into database | 1
|  | Generate release artifacts | 6
|  | Generate change log | 2
|  | Generate CSVs | 1
|  | Generate documentation spreadsheet | 2
|  | Generate statistics | 1
|  | Miscellaneous | 5
|  | Update CMF Tool | 2
|  | General support | 3
|  | NIEM Toolbox | 4.5
|  | User interfaces | 4.5
|  | Add new release artifact transformations | 0.5
|  | Model QA UI | 2
|  | Change request QA UI | 0.5
|  | Version statistics UI | 0.5
|  | Load database changes UI | 1
|  | NTAC Support | 6
|  | Meetings | 3
|  | NTAC Support (Tom) | 2
|  | NTAC Support (Christina) | 1
|  | Specifications | 3
|  | Message Specification Guidance feedback (Tom) | 2
|  | Message Specification Guidance feedback (Christina) | 1
|  | Miscellaneous | 5
|  | Miscellaneous | 5
|  | Training updates | 3
|  | Other | 2
|  | Grand Total | 54

## Data
Category | Group | Item | Est (days) | Lead | Comments | 100000 | 240 | 416.6667 | est hours | 52.0833 | est days | -1.9167
NIEM 6.1 PSD01 | Add new domains |  |  |  | Estimate assumes a lot of the modeling work has been done with Kamran
NIEM 6.1 PSD01 | Add new domains | Forensics | 1.5 | Christina
NIEM 6.1 PSD01 | Add new domains | Identity Management | 1.5 | Christina
NIEM 6.1 PSD01 | Add new domains | Analytical Laboratory | 1.5 | Christina
NIEM 6.1 PSD01 | Update existing content |  |  |  | Estimate is a guess. Scope of 6.1 changes unknown. Leverages new QA functionality.
NIEM 6.1 PSD01 | Update existing content | MilOps (EMS CR) | 0.5 | Christina
NIEM 6.1 PSD01 | Update existing content | Biometrics | 1 | Christina
NIEM 6.1 PSD01 | Update existing content | FBI code updates | 1 | Christina
NIEM 6.1 PSD01 | Update existing content | Other (TBD) | 1.5 | Christina
NIEM 6.1 PSD01 | Other model tasks
NIEM 6.1 PSD01 | Other model tasks | Facilitate or assist in public review meetings | 1 | Christina | Required by OASIS to make content changes
NIEM 6.1 PSD01 | Other model tasks | Update specification document | 1 | Christina
NIEM 6.1 PSD01 | Other model tasks | Update websites | 1 | Christina
NIEM 6.1 PSD01 | Other model tasks | Miscellaneous | 1.5 | Christina
NIEM API 2.0 | QA
NIEM API 2.0 | QA | Implement model QA | 3 | Christina | Check for potential issues that are not errors and wouldn't be caught by NDR conformance tests, e.g., empty types, abstract elements without substitutions.
NIEM API 2.0 | QA | Implement change request spreadsheet QA | 3 | Christina | Check change request spreadsheets for format errors that would prevent content from being loaded and for common modeling errors
NIEM API 2.0 | Update database content
NIEM API 2.0 | Update database content | Initialize new version | 0.5 | Christina | Get guidance from NTAC on how new versions should be initialized. Update all version numbers (URIs) to the new version? Just domains?
NIEM API 2.0 | Update database content | Implement user permissions | 3 | Christina
NIEM API 2.0 | Update database content | Load change request spreadsheet | 3 | Christina
NIEM API 2.0 | Update database content | Load migration rules into database | 1 | Christina | Load a change request spreadsheet using operation code "map" to create forward and backward migration rules between versions of a component.
NIEM API 2.0 | Update database content | Load CMF into database | 1 | Christina
NIEM API 2.0 | Generate release artifacts
NIEM API 2.0 | Generate release artifacts | Generate documentation spreadsheet | 2 | Christina | Build a transformation from CMF to provide users with human-readable documentation of a model version in a spreadsheet.
NIEM API 2.0 | Generate release artifacts | Generate change log | 2 | Christina | Leverage migration rules to shows what's been added to, removed from, and changed in a version. Highlight fields that have changed (e.g., name, definition)
NIEM API 2.0 | Generate release artifacts | Generate CSVs | 1 | Christina | Build a transformation from CMF to provide developers with easily-parseable CSVs so they can load NIEM components and codes into a database.
NIEM API 2.0 | Generate release artifacts | Generate statistics | 1 | Christina | Build a transformation from CMF to provide users with statistics about a model version, including a count of properties, types, and codes in total and by Core, domain, and code namespace.
NIEM API 2.0 | Miscellaneous
NIEM API 2.0 | Miscellaneous | Update CMF Tool | 2 | Christina | Update to latest version of CMF Tool. Leverage new conformance validation functionality when available.
NIEM API 2.0 | Miscellaneous | General support | 3 | Christina | Library updates, bug fixes, etc.
NIEM Toolbox | User interfaces
NIEM Toolbox | User interfaces | Add new release artifact transformations | 0.5 | Christina
NIEM Toolbox | User interfaces | Model QA UI | 2 | Christina | Download report or view results
NIEM Toolbox | User interfaces | Change request QA UI | 0.5 | Christina | Download report or view results
NIEM Toolbox | User interfaces | Version statistics UI | 0.5 | Christina | Download report or view results
NIEM Toolbox | User interfaces | Load database changes UI | 1 | Christina
NTAC Support | Meetings
NTAC Support | Meetings | NTAC Support (Tom) | 2 | Tom
NTAC Support | Meetings | NTAC Support (Christina) | 1 | Christina
NTAC Support | Specifications
NTAC Support | Specifications | Message Specification Guidance feedback (Tom) | 2 | Tom
NTAC Support | Specifications | Message Specification Guidance feedback (Christina) | 1 | Christina
Miscellaneous | Miscellaneous
Miscellaneous | Miscellaneous | Training updates | 3 | Tom | Update training with new features in NIEM Toolbox, etc.
Miscellaneous | Miscellaneous | Other | 2 | Tom
Total |  |  | 54

## 2024 (hidden)
Category | Item | Old Est. (days) | New Est. (days) | Person | Comments
NIEM 6.0 | NIEM Model Version 6.0
NIEM 6.0 | PS 02
NIEM 6.0 | Update 6.0 artifacts and publish | n/a | 1 | Christina | Update structures schema based on NTAC changes, and update the specification document for PS 02. Submit to the PGB for approval and update websites.
NIEM 6.0 | OS 01
NIEM 6.0 | Manage model changes through the OASIS Specification process | 5 | 2 | Christina | Depends if there is feedback that needs to be resolved during the 60-day Public Review process. Could require less or more time, depending on what we receive.
NIEM 6.0 | NIEM 6.0 Tools
NIEM 6.0 | Search and Subset tool + Subset Migration tool
NIEM 6.0 | Build the new open source NIEM Toolbox Search and Subset tool Build the new open source NIEM Toolbox Migration tool | 20 | 13 | Christina | Still pending: - Finish loading NIEM 6.0 data and migration rules - Build search UI on NIEM Toolbox - Build property and type details UI on NIEM Toolbox - Build subset UI on NIEM Toolbox - Finish migration UI on NIEM Toolbox
NIEM 6.0 | Conformance tool
NIEM 6.0 | Stand up new open source Conformance Tool on NIEM Toolbox, leveraging NIEM API 2.0 | 6 | 0.5 | Christina | Remaining: - Finish UI for NIEM Toolbox validation
NIEM 6.0 | NIEM 6.0 Technical Specifications
NIEM 6.0 | NDR Specification |  |  |  | Dr. Scott has the lead. Hours dropped assuming more of a review role.
NIEM 6.0 | Support | 10 | 5 | Tom
NIEM 6.0 | Support | 10 | 5 | Christina
NIEM 6.0 | NIEM JSON Guidance
NIEM 6.0 | Lead | 5 | 2 | Tom
NIEM 6.0 | Support | 2 | 0.5 | Christina
NIEM 6.0 | Conformance Specification |  |  |  | Original hours dropped assuming someone else loads the data into the OASIS templates and makes basic 6.0 updates.
NIEM 6.0 | Support | 2 | 0.5 | Tom | Small specification. Minor text updates for 6.0. Need to get it into the OASIS specification template for the first time.
NIEM 6.0 | Support | 0.5 | 0.5 | Christina
NIEM 6.0 | Code Lists Specification |  |  |  | Original hours dropped assuming someone else loads the data into the OASIS templates and makes basic 6.0 updates.
NIEM 6.0 | Support | 3 | 0.5 | Tom | Bigger specification than Conformance or CTAS. Minor text and schema updates for 6.0. Need to get it into the OASIS specification template for the first time.
NIEM 6.0 | Support | 0.5 | 0.5 | Christina
NIEM 6.0 | CTAS Specification |  |  |  | Original hours dropped assuming someone else loads the data into the OASIS templates and makes basic 6.0 updates.
NIEM 6.0 | Support | 1 | 0.5 | Tom | Small specification. Minor text and schema updates for 6.0. Already in the OASIS specificaiton template with version 3.0 earlier this year.
NIEM 6.0 | Support | 0.5 | 0.5 | Christina
NIEM 6.0 | Message Specification Guidance
NIEM 6.0 | Support | 10 | 5 | Tom
NIEM 6.0 | Support | 5 | 3 | Christina
MOMS 6.0 | NIEM 6.0 Tools |  |  |  | Note that this task is only for the MilOps contact and is not NIEMOpen work.
NIEM 6.0 | Lead |  | 3 | Christina | Update existing MOMS content with the NIEM 6.0 / OASIS updates. Update the database in preparation for when the new tools are ready. Note that the new search and subset tool is not ready, so MOMS tool support will not be available until that time.
NIEM 6.0 | Support |  | 1 | Chuck | Review package.
Total |  | 80.5 | 44