## POAM
CJCSI Project Plan
Project AO: Lavdjola Farrington
Target Date: | May 1st 2023
# | Goals | Action Items | Assigned to | Status | Start Date | Completion Date | Description | Notes
1 | Get Approval from Mr. Whitehead |  | Lavdjola Farrington |  | 2022-07-01 | 2022-08-29 | Pitch to DD the importance of having a CJCSI for MILOPS Domain and receive verbal approval to continue the work.
|  | 1.1 Develop slides for the brief |  |  | 2022-07-01 | 2022-08-29 |  | Discus the pros / cons of a CJCSI. How often does it need to be maintained? Why a CJCSI and not a DODI, or military std. What is the purpose of the CJCSI? Who is the audience of this document and how will it serve them and us (NIEM / JS). How does it benefit NIEM and JADC2. How many slides? Share the timeline on one of the slides, ( a different timeline than this that allows us as a team more time. ) Share and receive input from the CJCSI Team on the slides. How to get through J8 for approval as they are the gatekeeprs for taskers and have an issue with NIEM.
|  | 1.2 Schedule a meeting with Mr. Whitehead |  |  | 2022-07-01 | 2022-08-29 |  | Duration of the Meeting? 30 min
1 | Establish a workshop |  | Lavdjola Farrington |  | 2022-09-14 | 2022-10-27 | To determine the purpose of the CJCSI and draft the document.
|  | 1.1 Determine the key members | [5 empty] | Rodney Mccoy, Jack Dickerson, Shunda Woodhouse
|  | 1.2 Determine frequency of the workshop | [5 empty] | Conduct workshops every two weeks on Mondays. If needed, move to once a week.
|  | 1.3 Determine Location of the workshop |  |  |  |  | Via TEAMS | Create a team in TEAMS and invite all the key members.
1.4 Determine the agenda of the 1st workshop
1.4.1 Share with the team slides for Mr. Whitehead
2 | Initiate the 1st Draft |  | CJCSI Team |  | 2022-11-02 | 2023-02-23
2.1 Determine the purpose
2.2 Tittle
2.3 Applicability
2.4 Policy
2.5 Releasibility
2.6 Effective Date
2.7 Enclosures
2.8 Definitions / Glossary
3 | Internal Informal DSD Staffing |  | Lavdjola Farrington |  | 2023-03-27 | 2023-05-17
|  | 1. Consolidate Division Input | CJCSI Team
4 | AO JSAP Internal/External Coordination |  | Lavdjola Farrington |  | 2023-06-17 | 2023-08-10
4.1 Final Draft For Staffing
4.2 CRM
4.3 Form 136
4.4 Determine organizations to staff to
|  | 4.5 Staff via TMT | Beth Smalley
4.6 Receive inputs
4.7 Adjudicate inputs
5 | Flag / SES Staffing? |  |  |  | 2023-11-13 | 2023-12-28
1. Adjudicate any new comment
6 | Send to IMD for Review / Edit |  | Lavdjola Farrington |  | 2024-01-05 | 2024-03-19
7 | Final Document to J-Dir Approval Chain |  | Lavdjola Farrington |  | 2024-04-20 | 2024-05-01
8 | IMD publishes PDF format |  | IMD |  | 2024-06-01 | 2024-07-01

## my notes
1 Ask right questions | Why is this project needed? | Does this align with organizational goals?