## Sheet1
| Tasks | Responsibility | Target Date (start) | Completion Date | Notes
1 | Submit Statements of Use to PGB |  | 2025-09-01 | 2025-09-11
| 1- NDR 6.0 PS01 & NIEM Model Version 6.0 PS02 | Cabral | 2025-09-05
| 2 - NDR 6.0 PS01 & NIEM Model Version 6.0 PS02 | Renner | 2025-09-05
| 3 - NDR 6.0 PS01 & NIEM Model Version 6.0 PS02 | GTRI | 2025-09-05 | 2025-09-05
| Call for simple majoriy vote on SoUs | Sullivan | 2025-09-05 | 2025-09-05
2 | SoU Approved by PGB as acceptable wrt specification | PGB | 2025-09-5 to 2025-09-11 | 2025-09-11 | Simple majority vote
3 | PGB Simple Majority Vote to conduct Public Review
4 | A (MINIMUM) 60 DAY Public Review: Request a first Public Review | Wormeli |  |  | https://www.oasis-open.org/project-administration-support-requests/form-request-a-first-public-review/
5 | Member Wide Ballot | Wormeli
5a | 2 week notification of member wide ballot | Wormeli |  |  | Where is this notification made, who submits?
5b | Request Member-wide 14 day ballot to approve the COS as an OASIS Standard | Wormeli |  |  | https://www.oasis-open.org/project-administration-support-requests/form-request-a-special-majority-vote-to-approve-a-candidate-for-oasis-standard/
5c | Member Wide Vote (14 days) | Member Wide